## Resource Model
Resource Model
All values are formulas — change source data and this sheet recalculates
Refresh required: Capacity Heatmap, Gantt, weekly role heatmap, demand column, project duration estimates, suggested dates
Time Allocation
Base Hours/Week
Admin %
Support/Break-Fix %
Project %
Project Hrs/Person/Wk
Max Projects/Person
SDLC Phase Weights
Phase | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total
Weight
Role Effort by SDLC Phase
Role | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total
Project Manager
DBA
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
Developer
Infrastructure
WMS Consultant
Per-Person Capacity
Role | Headcount | Team Supply (hrs/wk) | Per-Person (hrs/wk)
Project Manager
DBA
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
Developer
Infrastructure
WMS Consultant
TOTAL
Per-Project Resource Breakdown
Only the Project ID is entered — all other values are formulas referencing source sheets
ETE-124 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-37 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
IT Functional Analyst
Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-97 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-68 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-19 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-83 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
TOTAL
Reconciliation
Phase Duration (days)
ETE-48 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
Project Manager
IT Business Analyst/SME
TOTAL
Reconciliation
Phase Duration (days)
ETE-100 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-49 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-7 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-16 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
IT Functional Analyst
IT Tech Analyst/Developer
TOTAL
Reconciliation
Phase Duration (days)
ETE-52 |  |  | Priority: |  | Est Hrs:
| Alloc % | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total Hrs | Days
Phase Hours
IT Business Analyst/SME
Developer
TOTAL
Reconciliation
Phase Duration (days)

## Capacity Summary
ETE IT PMO — Capacity Summary
All supply/headcount values are formulas — change Team Roster and this sheet recalculates
Team Size |  | Active Projects |  | Weekly Supply |  | Weekly Demand |  | Utilization
15
Supply vs. Demand by Role
Role | Headcount | Per-Person (hrs/wk) | Team Supply (hrs/wk) | Team Demand (hrs/wk) | Gap (hrs/wk) | Utilization | Status
Project Manager |  |  |  | 0
DBA |  |  |  | 0
IT Business Analyst/SME |  |  |  | 0
IT Functional Analyst |  |  |  | 0
IT Tech Analyst/Developer |  |  |  | 0
Developer |  |  |  | 0
Infrastructure |  |  |  | 0
WMS Consultant |  |  |  | 0
TOTAL
Active Projects — Bottom-Up Duration Estimates
ID | Project | Priority | Est Hrs | Allocated | Duration (days) | Bottleneck Role | Start | End
ETE-124 | Clean Up Return Loads | Highest | 200 | 220 |  | IT Business Analyst/SME | TBD | TBD
ETE-37 | Magic Search in BuyETE | Highest | 40 | 40 |  | IT Business Analyst/SME | TBD | TBD
ETE-97 | Standard Order Process Notifications | Highest | 200 | 170 |  | IT Business Analyst/SME | TBD | TBD
ETE-68 | Catalog API Rust2Python | High | 640 | 544 |  | IT Business Analyst/SME | 11/17/2025 | 04/24/2026
ETE-19 | Changes to AR Aging Report | High | 120 | 120 |  | IT Business Analyst/SME | 02/23/2026 | 04/17/2026
ETE-83 | Customer Master Data Cleanup | High | 1480 | 148 |  | IT Business Analyst/SME | 10/14/2025 | 06/01/2026
ETE-48 | System Connection Syteline-VKS | High | 240 | 84 |  | IT Business Analyst/SME | 02/15/2026 | 06/30/2026
ETE-100 | ATSG Expired Members Self-Payment | Medium | 200 | 170 |  | IT Business Analyst/SME | TBD | TBD
ETE-49 | Marketing: STE Rewards Tier | Medium | 240 | 204 |  | IT Business Analyst/SME | TBD | TBD
ETE-7 | Outsourced Unit Core Accounting | Medium | 640 | 640 |  | IT Business Analyst/SME | TBD | TBD
ETE-16 | Partial Pay w/ CC from WMERP | Medium | 120 | 120 |  | IT Business Analyst/SME | TBD | TBD
ETE-52 | SWIMS/Syteline Reporting | Medium | 40 | 34 |  | IT Business Analyst/SME | TBD | TBD

## Role Capacity Planner
ETE IT PMO — Role Capacity Planner
Scenario table uses formulas — change Team Roster and scenarios recalculate
Headcount Scenario Analysis
Shows current state and impact of adding +1, +2, or +3 people per role
Role | Current Headcount | Per-Person (hrs/wk) | Team Supply (hrs/wk) | Demand (hrs/wk) | Current Util % | Status | +1 Person Supply | +1 Person Util % | +1 Status | +2 People Supply | +2 People Util % | +2 Status | +3 People Supply | +3 People Util % | +3 Status
Project Manager |  |  |  | 0
DBA |  |  |  | 0
IT Business Analyst/SME |  |  |  | 0
IT Functional Analyst |  |  |  | 0
IT Tech Analyst/Developer |  |  |  | 0
Developer |  |  |  | 0
Infrastructure |  |  |  | 0
WMS Consultant |  |  |  | 0
Impact on Project Durations (days)
How project durations change if we add 1 person to a role (bottleneck relief)
ID | Project | Est Hrs | Current Days | +1 Project Manager Days | +1 DBA Days | +1 Business Analyst Days | +1 Functional Analyst Days | +1 Tech Analyst Days | +1 Developer Days | +1 Infrastructure Days | +1 WMS Consultant Days
ETE-124 | Clean Up Return Loads | 200
ETE-37 | Magic Search in BuyETE | 40
ETE-97 | Standard Order Process Notifications | 200
ETE-68 | Catalog API Rust2Python | 640
ETE-19 | Changes to AR Aging Report | 120
ETE-83 | Customer Master Data Cleanup | 1480
ETE-48 | System Connection Syteline-VKS | 240
ETE-100 | ATSG Expired Members Self-Payment | 200
ETE-49 | Marketing: STE Rewards Tier | 240
ETE-7 | Outsourced Unit Core Accounting | 640
ETE-16 | Partial Pay w/ CC from WMERP | 120
ETE-52 | SWIMS/Syteline Reporting | 40
Weekly Role Utilization Heatmap
Role-level utilization by week — shows when role groups get hot
Overloaded (>100%) | At Capacity (80-100%) | Healthy (<80%)
Role | Headcount | Supply (hrs/wk) | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08 | 06/15 | 06/22 | 06/29 | 07/06 | 07/13 | 07/20 | 07/27 | 08/03 | 08/10 | 08/17 | 08/24 | 08/31 | 09/07 | 09/14 | 09/21 | 09/28
Project Manager | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT Business Analyst/SME | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT Functional Analyst | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT Tech Analyst/Developer | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Portfolio
ETE IT PMO — Project Portfolio
ID | Project Name | Type | Business Portfolio | Sponsor/Leader | Project Health | % Complete | Priority | Start Date | Est. End Date | Actual/Updated End | Team | PM | BA | Functional | Technical | Developer | T-Shirt Size | Est. Hours | Est. Cost Range | BA % | Functional % | Technical % | Developer % | Infrastructure % | DBA % | PM % | WMS % | Notes | Sort Order
ETE-83 | Customer Master Data Cleanup | Key Initiative | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 15% | High | 2025-10-14 | 2026-06-01 |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young | XXL: > 640 Hours | 1480 |  | 10% | [7 empty] | Completed Q1
ETE-48 | System Connection Syteline-VKS | Key Initiative | Engineering | Ray Trumble | 🟢 ON TRACK | 10% | High | 2026-02-15 | 2026-06-30 |  | Synnergie | Emily Fridley | Audrey Debaere |  |  | Alex Young | L: 160-320 Hours | 240 |  | 10% | [5 empty] | 25%
ETE-68 | Catalog API Rust2Python | Key Initiative | Information Technology | Jim Koscielniak | 🟢 ON TRACK | 13% | High | 2025-11-17 | 2026-04-24 |  | Systems Applications | Emily Fridley | Audrey Debaere |  | Colin Olson | Alex Young | XXL: > 640 Hours | 640 |  | 10% |  |  | 75%
ETE-43 | Data Security - Microsoft Purview | Key Initiative | Information Technology | Jim Koscielniak | 🟢 ON TRACK | 0% | High | 2026-02-02 | 2026-06-30 |  | Infrastructure | Emily Fridley | Audrey Debaere |  |  | Alex Young |  | 0 |  | 10%
ETE-19 | Changes to AR Aging Report | Enhancement | Finance | Tom Newell | 🟢 ON TRACK | 0% | High | 2026-02-23 | 2026-04-17 |  | Synnergie | Emily Fridley | Audrey Debaere | Ajay Kumar | Bhavya Reddy | Alex Young | M: 80-160 Hours | 120 |  | 10% | 25% | 65%
ETE-49 | Marketing: STE Rewards Tier | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 0% | Medium |  |  |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young | L: 160-320 Hours | 240 |  | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0%
ETE-7 | Outsourced Unit Core Accounting | Enhancement | Finance | Tom Newell | 📋 NEEDS FUNCTIONAL SPEC | 0% | Medium |  |  |  | Synnergie | Emily Fridley | Audrey Debaere |  |  | Alex Young | XXL: > 640 Hours | 640 |  | 10% | 25% | 65% | 0% | 0% | 0% | 0% | 0% | 8-9 month project
ETE-52 | SWIMS/Syteline Reporting | Enhancement | Supply Chain | Jon Besherse | 📋 NEEDS TECHNICAL SPEC | 0% | Medium |  |  |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young | S: < 80 Hours | 40 |  | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0%
ETE-16 | Partial Pay w/ CC from WMERP | Enhancement | Finance | Tom Newell | ⚪ NOT STARTED | 0% | Medium |  |  |  | Synnergie | Emily Fridley | Audrey Debaere |  |  | Alex Young | M: 80-160 Hours | 120 |  | 10% | 25% | 65% | 0% | 0% | 0% | 0% | 0%
ETE-37 | Magic Search in BuyETE | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 0% | Highest |  |  |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young | S: < 80 Hours | 40 |  | 10% | 25% | 0% | 65% | 0% | 0% | 0% | 0%
ETE-97 | Standard Order Process Notifications | Enhancement | Sales & Distribution | Tom Vierling | ⚪ NOT STARTED | 0% | Highest |  |  |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young |  | 200 |  | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0%
ETE-100 | ATSG Expired Members Self-Payment | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS FUNCTIONAL SPEC | 0% | Medium |  |  |  | Systems Applications | Emily Fridley | Audrey Debaere |  |  | Alex Young |  | 200 |  | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0%
ETE-124 | Clean Up Return Loads | Enhancement | Finance | Tom Newell | 📋 NEEDS TECHNICAL SPEC | 0% | Highest |  |  |  | Synnergie | Emily Fridley | Audrey Debaere |  |  | Alex Young |  | 200 |  | 10% | 25% | 75% | 0% | 0% | 0% | 0% | 0%
ETE-58 | Transfer Order Moved Items to Transit Location | Enhancement | Finance | Jim Young | ⏸️ POSTPONED | 0%
ETE-51 | RMA Credit Memo on Ghost Check-In | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0%
ETE-59 | Reconcile BridgePay CC Transactions | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0%
ETE-60 | EDI Payments Not Posting on Background | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0%
ETE-61 | Accum Deposits Received Field | Bug | Finance | Tom Newell | ⏸️ POSTPONED | 0%
ETE-86 | Allow TCM Core Receiving to Post | Enhancement | Engineering | Ray Trumble | ⏸️ POSTPONED | 0%
ETE-34 | Salesforce BDR Application & Process Implementation | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0%
ETE-35 | BuyETE Ability for Customers to Save Quotes | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0%
ETE-33 | EDI 3PL Locations | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0% | High |  |  |  | Systems Applications |  | Jim Young |  |  |  | M: 80-160 Hours | 120
ETE-67 | Avalara Tax Issues | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | Highest | 2026-02-04 | 2026-02-27 |  | Synnergie |  | Audrey Debaere | Deepak Gudwani | Sangamesh Koti |  | M: 80-160 Hours | 120 |  | 10% | 25% | 75%
ETE-14 | Installed Return RMA Type | Enhancement | Supply Chain | Jon Besherse | ✅ COMPLETE | 100% | Highest | 2026-03-02 | 2026-03-20 |  | Synnergie |  | Audrey Debaere |  |  |  | M: 80-160 Hours | 120 |  | 10% | 25% | 65%
ETE-70 | Nutanix (Replace VMware) | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | Highest | 2025-12-01 | 2026-03-21 |  | Infrastructure |  |  |  | Michael House |  |  | 120 |  | 10% |  |  |  | 50%
ETE-65 | Rebuild Vendor Portal | Enhancement | Sales & Distribution | Tom Vierling | ✅ COMPLETE | 100% | High | 2025-10-27 | 2026-01-09 | 2026-02-15 | Systems Applications |  | Jim Young |  | Jonathon Gonzalez |  | S: < 80 Hours | 60 | 11895
ETE-69 | Core Plan Optimization | Key Initiative | Supply Chain | Jon Besherse | ✅ COMPLETE | 100% | High | 2025-11-12 | 2026-01-23 | 2026-01-23 | Synnergie |  | Audrey Debaere |  | Ravindra Reddy |  | L: 160-320 Hours | 360 | 16120
ETE-31 | Restocking Fees Added to RMA Credit Memo | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | High | 2024-12-22 | 2026-02-06 | 2026-02-28 | Synnergie |  | Audrey Debaere |  | Bhavya Reddy |  | L: 160-320 Hours | 310 | 1625
ETE-45 | VB Bin Printer Integration | Enhancement | Engineering | Ray Trumble | ✅ COMPLETE | 100% | High | 2025-10-20 | 2026-02-20 | 2026-02-20 | Synnergie |  | Cristian Varelas |  | Sangamesh Koti |  | M: 80-160 Hours | 160 | 260
ETE-42 | Gear Screen - Improved Production Oversight | Key Initiative | Production | Ari Rosengarten | ✅ COMPLETE | 100% | High | 2026-01-12 | 2026-02-05 | 2026-02-28 | Synnergie |  | Cristian Varelas |  | Vishnu Premen |  | M: 80-160 Hours | 120 | [9 empty] | NAPA not ready
ETE-72 | Fortigate ZTNA - EMS Setup | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | High | 2025-12-12 | 2025-12-31 | 2026-02-27 | Infrastructure |  |  |  | Justin Senour |  |  | 0
ETE-71 | One Drive Migration | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | High | 2025-12-22 | 2026-02-06 | 2026-02-15 | Infrastructure |  |  |  | Michael House |  |  | 0
ETE-87 | Production Dashboard | Enhancement | Production | Ari Rosengarten | ✅ COMPLETE | 100% | High |  |  |  | Systems Applications | [5 empty] | S: < 80 Hours | 40
ETE-88 | Return Load Phase 2 | Key Initiative | Finance | Tom Newell | ✅ COMPLETE | 100% | High | 2025-10-27 | 2025-12-29 | 2026-01-09 | Synnergie |  | Audrey Debaere |  | Sangamesh Koti |  |  | 320
ETE-73 | Teal Parts Daily Inventory Feed | Enhancement | Sales & Distribution | Tom Vierling | ✅ COMPLETE | 100% | Highest |  |  |  | Systems Applications |  | Cristian Varelas |  |  |  | S: < 80 Hours | 40
ETE-10 | Upload Utility for Planning Fields | Enhancement | Supply Chain | Tom Green | ✅ COMPLETE | 10% | Highest |  |  |  | Synnergie | Emily Fridley | Audrey Debaere |  |  | Alex Young | S: < 80 Hours | 80
ETE-32 | Form: Cash App SQL Fix | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | High |  |  |  | Synnergie |  | Audrey Debaere |  |  |  | L: 160-320 Hours | 320
ETE-76 | FedEx Web Services API | Enhancement | Information Technology | Jim Koscielniak | ✅ COMPLETE | 0% | High | 2026-03-03 | 2026-03-13 |  | Systems Applications | Emily Fridley | Audrey Debaere |  | Alex Young | Alex Young | S: < 80 Hours | 40

## Team Roster
ETE IT PMO — Team Roster & Capacity
Resource | Role | Team | Vendor | Resource Classification | Rate/Hour | Weekly Hrs Available | Support Reserve % | Project Capacity % | Support Reserve (hrs/wk) | Project Capacity (hrs/wk)
Ajay Kumar | Functional | ERP | Synnergie | MSA | 65 | 35 | 40%
Ravindra Reddy | Technical | ERP | Synnergie | MSA | 65 | 35 | 40%
Vishnu Premen | Technical | ERP | Synnergie |  | 65 | 35 | 40%
Deepak Gudwani | Functional | ERP | Synnergie |  | 65 | 35 | 40%
Sangamesh Koti | Technical | ERP | Synnergie | T&M | 65 | 35 | 0%
Bhavya Reddy | Technical | ERP | Synnergie |  | 65 | 35 | 0%
Sarath Yeturu | Technical | ERP | Synnergie | MSA | 65 | 35 | 60%
Vinod Bollepally | DBA | ERP | Synnergie | MSA | 65 | 35 | 80%
Jim Young | Business Analyst | Business Analysts | ETE |  | 65 | 40 | 60%
Alex Young | Developer | Systems Applications | ETE |  | 65 | 25 | 50%
Nick Smith | Developer | Systems Applications | ETE |  | 65 | 25 | 40%
Colin Olson | Developer | Systems Applications | ETE |  | 65 | 25 | 10%
Jonathon Gonzalez | Developer | Systems Applications | ETE |  | 65 | 25 | 25%
Audrey Debaere | Business Analyst | Business Analysts | ETE |  | 65 | 35 | 50%
Cristian Varelas | Business Analyst | Business Analysts | ETE |  | 65 | 35 | 20%
Ryan Picado | Business Analyst | Business Analysts | ETE |  | 65 | 35 | 50%
Emily Fridley | Project Manager | PMO | ETE |  | 65 | 35 | 50%
Brett Anderson | Project Manager | PMO | ETE |  | 65 | 35 | 25%
Bettina Kotico | Project Manager | PMO | Kayana | T&M | 65 | 32 | 68%
Donna Wiedemeier | WMS Consultant | WMS | Watermark | T&M | 65 | 35 | 60%
Justin Senour | Infrastructure | Infrastructure | ETE |  | 65 | 40 | 60%
Michael House | Infrastructure | Infrastructure | ETE |  | 65 | 40 | 60%
Andrew Shaefer | Infrastructure | Infrastructure | ETE |  | 65 | 40 | 60%
TOTALS

## RM_Assumptions
ETE IT PMO — Resource Model Assumptions
All blue inputs are configurable. Change values to run scenarios.
TIME ALLOCATION MODEL
Parameter | Value | Unit | Notes
Base Hours / Week | 40 | hrs | Standard work week
Admin Allocation | 10% | % | Meetings, email, admin tasks
Break/Fix Allocation | 10% | % | Support tickets, break/fix work
Project Allocation | 80% | % | Time available for project work
Available Project Hrs / Person / Wk |  | hrs | Base Hrs × Project %
Allocation Check (must = 100%)
Max Projects / Person | 3 | projects | Constraint: no one on more than 3
SDLC PHASE WEIGHTS
| Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total
% of Project Effort | 10% | 10% | 15% | 30% | 20% | 15%
ROLE EFFORT BY SDLC PHASE
% of phase effort per role (rows don't need to sum to 100% — each role works a share of each phase independently)
Role | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Avg Effort
PM | 10% | 25% | 15% | 20% | 20% | 10%
DBA | 5% | 10% | 30% | 25% | 20% | 10%
IT Business Analyst/SME | 30% | 20% | 20% | 10% | 15% | 5%
IT Functional Analyst | 20% | 10% | 30% | 15% | 15% | 10%
IT Tech Analyst/Developer | 5% | 10% | 20% | 40% | 15% | 10%
Developer | 0% | 5% | 10% | 50% | 25% | 10%
Infrastructure | 5% | 10% | 15% | 20% | 15% | 35%
WMS Consultant | 10% | 15% | 10% | 10% | 5% | 50%
Phase Total (all roles)
SUPPLY: TEAM CAPACITY BY ROLE
Role | Headcount | Hrs/Wk (Gross) | Project Hrs/Wk | Notes
PM |  |  |  | Roster role: "Project Manager"
DBA |  |  |  | Roster role: "DBA"
IT Business Analyst/SME |  |  |  | Roster role: "Business Analyst"
IT Functional Analyst |  |  |  | Roster role: "Functional"
IT Tech Analyst/Developer |  |  |  | Roster role: "Technical"
Developer |  |  |  | Roster role: "Developer"
Infrastructure |  |  |  | Roster role: "Infrastructure"
WMS Consultant |  |  |  | Roster role: "WMS Consultant"
TOTAL

## Capacity Heatmap
ETE IT PMO — Weekly Capacity Heatmap (Per Person)
Overloaded (>100%) | At Capacity (80-100%) | Healthy (<80%)
Resource | Role | Team | Capacity (hrs/wk) | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08 | 06/15 | 06/22 | 06/29 | 07/06 | 07/13 | 07/20 | 07/27 | 08/03 | 08/10 | 08/17 | 08/24 | 08/31 | 09/07 | 09/14 | 09/21 | 09/28
Bettina Kotico | Project Manager | PMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brett Anderson | Project Manager | PMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emily Fridley | Project Manager | PMO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vinod Bollepally | DBA | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Audrey Debaere | Business Analyst | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cristian Varelas | Business Analyst | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jim Young | Business Analyst | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ryan Picado | Business Analyst | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ajay Kumar | Functional | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deepak Gudwani | Functional | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bhavya Reddy | Technical | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ravindra Reddy | Technical | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sangamesh Koti | Technical | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sarath Yeturu | Technical | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vishnu Premen | Technical | ERP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alex Young | Developer | Systems Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colin Olson | Developer | Systems Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jonathon Gonzalez | Developer | Systems Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nick Smith | Developer | Systems Applications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andrew Shaefer | Infrastructure | Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Justin Senour | Infrastructure | Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael House | Infrastructure | Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Donna Wiedemeier | WMS Consultant | WMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## RM_Gantt
ETE IT PMO — Project Gantt Chart
Generated: 03/31/2026 ¦ Color = priority
NOW
ID | Project Name | Priority | Est Hrs | Start | End | Dur | 10/13 | 10/20 | 10/27 | 11/03 | 11/10 | 11/17 | 11/24 | 12/01 | 12/08 | 12/15 | 12/22 | 12/29 | 01/05 | 01/12 | 01/19 | 01/26 | 02/02 | 02/09 | 02/16 | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08 | 06/15 | 06/22 | 06/29 | 07/06 | 07/13 | 07/20 | 07/27
ETE-124 | Clean Up Return Loads | Highest | 200 | TBD | TBD
ETE-37 | Magic Search in BuyETE | Highest | 40 | TBD | TBD
ETE-97 | Standard Order Process Notifications | Highest | 200 | TBD | TBD
ETE-10 | Upload Utility for Planning Fields | Highest | 80 | TBD | TBD
ETE-68 | Catalog API Rust2Python | High | 640 | 11/17/2025 | 04/24/2026 | 23w
ETE-19 | Changes to AR Aging Report | High | 120 | 02/23/2026 | 04/17/2026 | 8w
ETE-83 | Customer Master Data Cleanup | High | 1480 | 10/14/2025 | 06/01/2026 | 33w
ETE-76 | FedEx Web Services API | High | 40 | 03/03/2026 | 03/13/2026 | 1w
ETE-48 | System Connection Syteline-VKS | High | 240 | 02/15/2026 | 06/30/2026 | 19w
ETE-100 | ATSG Expired Members Self-Payment | Medium | 200 | TBD | TBD
ETE-49 | Marketing: STE Rewards Tier | Medium | 240 | TBD | TBD
ETE-7 | Outsourced Unit Core Accounting | Medium | 640 | TBD | TBD
ETE-16 | Partial Pay w/ CC from WMERP | Medium | 120 | TBD | TBD
ETE-52 | SWIMS/Syteline Reporting | Medium | 40 | TBD | TBD
Legend: | Highest |  | High |  | Medium |  | Low

## RM_Guide
ETE IT PMO — Resource Model Guide
A plain-English explanation of how the Resource Model works, what each sheet does, and how to use it.
THE BIG PICTURE
What is this? | A set of 4 connected sheets that answer: "Do we have enough people for all these projects, and when will we be in trouble?"
Why does it exist? | The Portfolio shows WHAT projects we have. The Resource Model shows WHETHER we can actually staff them — and when bottlenecks will hit.
Who should use it? | PMO leads for weekly planning, resource decisions, and "what if" scenario testing (hiring, project delays, reprioritization).
How do the sheets connect? | RM_Assumptions (rules) → RM_Demand (how much work) → RM_SupplyVsDemand (big picture) → RM_WeeklyHeatmap (when exactly).
What are the blue cells? | Any cell with a blue/light blue background is an INPUT you can change. These are your scenario levers — adjust them and the model recalculates automatically.
SHEET-BY-SHEET EXPLANATION
📋 RM_Assumptions | "What are our rules?" — This is the control panel for the whole model.
Time Allocation (rows 6-12) | Each person works 40 hrs/week, but not all of it goes to projects. Admin (10%) and Break/Fix support (10%) eat into that, leaving 80% = 32 hrs/week for project work. You can change these percentages.
SDLC Phase Weights (row 16) | A project isn't evenly spread. It's 10% Discovery → 10% Planning → 15% Design → 30% Build → 20% Test → 15% Deploy. These must add to 100%. Change them to match your actual project lifecycle.
Role Effort by Phase (rows 21-28) | THIS IS THE KEY INSIGHT. A DBA isn't equally busy throughout a project. They barely touch Discovery (5%) but are heavily loaded in Build (30%). A BA is the opposite — 30% in Discovery, only 10% in Build. These percentages drive the weekly demand spikes in the heatmap.
Team Supply (rows 30-38) | Auto-counts headcount and hours from the Team Roster. You don't edit these — they update when Team Roster changes.
📊 RM_Demand | "How much work is coming?" — Calculates total demand from active projects.
Active Projects (rows 6-18) | Automatically pulls all non-complete, non-postponed projects from the Portfolio. You don't edit these rows — they update when Portfolio changes.
Total Demand by Role (rows 24-30) | For each role, adds up: (Project Est. Hours × Role Allocation %) across all active projects. Shows you the total hours each role needs to deliver.
Project × Role Detail (rows 36-48) | A breakdown showing exactly how many hours each project needs from each role. Useful for seeing which projects are driving the most demand.
⚖️ RM_SupplyVsDemand | "Are we OK overall?" — A summary scorecard comparing supply to demand.
Capacity Scorecard (rows 5-7) | The headline numbers: Total Supply hrs/wk, Total Demand hrs/wk, Net Gap (+ means surplus, - means deficit), and Overall Utilization %.
By Role (rows 11-17) | Same comparison broken out by role. Color-coded: green = fine, yellow = tight, red = over capacity. This tells you WHERE the problem is.
Scenario Notes (rows 31-37) | A free-text area for documenting assumptions, decisions, and scenario notes from planning sessions.
🗓️ RM_WeeklyHeatmap | "WHEN are we in trouble?" — The action sheet you use in weekly planning.
Headcount Adjusters (rows 6-12) | Type a number in the blue "Add/Remove" cells to simulate hiring or losing staff. Type 1 next to DBA to test "what if we hire another DBA?" Type -1 to test losing someone. The heatmap recalculates instantly.
Project Timelines (rows 17-29) | Shows each active project's start/end dates (blue = editable). Change a date to test "what if we delay ETE-43 by a month?" or "what if we start ETE-49 sooner?" The heatmap recalculates.
The Heatmap (rows 34-40) | The payoff. Each cell shows utilization % for one role in one week. Green (<80%) = fine. Yellow (80-99%) = getting tight. Red (100%+) = overloaded, need to act. Demand shifts week-to-week because the model knows which SDLC phase each project is in.
HOW TO RUN SCENARIOS
"What if we hire another DBA?" | Go to RM_WeeklyHeatmap → cell C11 (DBA Add/Remove) → type 1. The DBA row in the heatmap will drop from red to green. If it works, you've justified the hire.
"What if we delay a project?" | Go to RM_WeeklyHeatmap → find the project in rows 17-29 → change its Start Date (column D) or End Date (column E). The heatmap will shift that project's demand to different weeks.
"What if a project takes longer?" | Push the End Date further out. The same total hours get spread over more weeks, so weekly demand drops — but it stays on the heatmap longer.
"What if we change how much BA time a project needs?" | Go to RM_Assumptions → Role Effort by Phase (rows 21-28) → adjust the BA row. This changes how much BA demand every project generates during each phase.
"What if we shift more time to admin?" | Go to RM_Assumptions → Time Allocation (rows 7-9) → increase Admin %, decrease Project %. Everyone's available project hours shrink, so utilization goes up across the board.
Reset everything | Set all Headcount Adjusters back to 0. The project dates will revert to Portfolio defaults on their own (they pull from Portfolio when not overridden).
READING THE HEATMAP COLORS
🟢 Green (under 80%) | This role has capacity. No action needed.
🟡 Yellow (80-99%) | At risk. A short burst of yellow (1-2 weeks) is OK — people can push through. But sustained yellow over 3+ weeks means you're running tight and any surprise will tip into red.
🔴 Red (100% or higher) | Over capacity. This role physically can't deliver everything assigned to them. Something has to give: hire more, delay a project, or reassign work. The higher the %, the worse it is (183% means you'd need almost 2x the people).
All zeros (0%) | Either no projects are active that week, or no projects need that role. Check if project dates are set correctly in the timeline section.
IMPORTANT NOTES
Projects with no dates | If a project in the Portfolio has no Start/End date, the heatmap defaults it to starting today with a 12-week duration. Once real dates are added to the Portfolio, it picks them up automatically.
Completed/Postponed projects | These are automatically excluded from all demand calculations. You don't need to remove them.
Phase totals over 100% | In RM_Assumptions, the Phase Total row may show >100%. This is correct — it means multiple roles work on the same phase. It's not a distribution (doesn't need to sum to 100%), it's effort intensity per role.
Headcount vs. Team Roster | Base headcount in the heatmap comes from Team Roster via RM_Assumptions. The Adjuster in the heatmap is a temporary "what if" — it doesn't change the actual roster.
Don't edit gray cells | Gray cells contain formulas. If you overwrite them, the model breaks. Only edit blue cells.
📅 RM_Gantt (Resource-Leveled Gantt) | "What's the recommended schedule?" — Shows projects rescheduled to avoid resource overloads.
What it does | Takes all 13 active projects, sorts them by priority (Highest first), and schedules them one by one. If adding a project would push any role over 100% capacity, it pushes that project's start date forward week-by-week until it fits.
Schedule Table (cols A-I) | Shows each project's original dates vs. adjusted dates. The "Shifted" column tells you how many weeks a project was pushed. Yellow-highlighted adjusted dates = the project moved.
Gantt Bars (cols J+) | Color-coded bars: Red = Highest priority, Yellow = High, Blue = Medium. Green ghost bars show where a shifted project was originally scheduled.
Key insight | The DBA is the binding constraint. All 5 Medium projects had to shift because of DBA overload. Highest and High priority projects kept their original dates.
⚠️ Important | This is a one-time snapshot, NOT a live formula. After changing headcount adjusters or project dates in RM_WeeklyHeatmap, ask Claude to regenerate the Gantt to get an updated recommended schedule.

## AI_Agent_Spec
ETE IT PMO — AI Resource Planning Agent: Technical Specification
Phase 1 MVP — Stateful AI agent for resource optimization, portfolio analysis, and decision support.
1. PROJECT OVERVIEW
Project Name | ETE IT PMO AI Resource Planning Agent
Version | Phase 1 MVP
Purpose | Build a persistent AI agent that reads the ETE IT PMO Excel workbook, understands the project portfolio and team capacity, runs constraint-based optimization for resource scheduling, and provides natural language recommendations via a chat interface. Excel remains the source of truth for data entry and executive/board reporting.
Problem Statement | The PMO team manually manages 40+ projects across 23 resources using Excel. Determining optimal project schedules, identifying resource bottlenecks, and running what-if scenarios requires navigating 6+ interconnected sheets with complex formulas. The team needs an intelligent layer that can answer capacity questions, flag risks, and recommend optimal schedules — while keeping Excel as the foundation.
Key Outcome | A PMO lead can ask: "Can we take on a new 400-hour project with 60% Developer allocation?" and get an immediate answer with impact analysis, trade-off options, and a recommended schedule — all grounded in real data from the Excel workbook.
Estimated Effort | 2-3 weeks with one Python developer familiar with APIs and basic cloud deployment.
Estimated Monthly Cost | ~$30-70/month (Claude API ~$20-50, hosting ~$10-20). No per-seat licensing.
2. EXCEL DATA MODEL — Source of Truth
Workbook | ETE_2026_IT_Budget_Tracker.xlsx (hosted on SharePoint/OneDrive)
Access Method | Option A: Microsoft Graph API (if on SharePoint — preferred for real-time access) Option B: openpyxl (Python library — reads .xlsx directly from file share) Option C: OneDrive sync + file watcher (simplest — watch local copy for changes)
2a. Project Portfolio Sheet
Range | Project Portfolio'!A3:AC42 (row 3 = headers, rows 4-42 = projects)
Key Columns | A: ID (e.g., ETE-83) ¦ B: Project Name ¦ C: Type ¦ D: Business Portfolio ¦ E: Sponsor/Leader ¦ F: Project Health (ON TRACK, NEEDS SPEC, NOT STARTED, POSTPONED) ¦ G: % Complete (0-100%) ¦ H: Priority (Highest/High/Medium/Low) ¦ I: Start Date ¦ J: Est. End Date ¦ R: Est. Hours ¦ T-AA: Role allocation percentages (BA%, Func%, Tech%, Dev%, Infra%, DBA%, PM%, WMS%)
Active Filter | Exclude: Project Health = POSTPONED, % Complete = 100%. Currently ~13 active of 40 total.
Priority Rule | ABSOLUTE: Highest > High > Medium > Low. Never delay Highest for Medium.
2b. Team Roster Sheet
Range | Team Roster'!A3:H26 (23 team members)
Key Columns | A: Resource name ¦ B: Role (PM, DBA, BA, Functional, Technical, Developer, Infrastructure, WMS) ¦ C: Team ¦ D: Vendor ¦ E: Classification (FTE/Contractor) ¦ F: Rate/Hour ¦ G: Weekly Hrs Available ¦ H: Support Reserve %
Current Team | 23 resources: 3 PM, 1 DBA, 4 BA/SME, 2 Functional, 5 Technical, 4 Developer, 3 Infrastructure, 1 WMS
2c. RM_Assumptions Sheet
Time Allocation | Admin 10% + Break/Fix 10% + Project 80% = 100%. Result: 32 project hrs/person/week.
SDLC Phase Weights | Discovery 10%, Planning 10%, Design 15%, Build 30%, Test 20%, Deploy 15% = 100%
Role Effort Matrix | 8 roles × 6 phases. Example: Developer = 0% Discovery → 5% Planning → 10% Design → 50% Build → 25% Test → 10% Deploy. This drives demand curves — each role's workload varies by project phase.
Critical Rule | Demand for a role is ZERO if the project's role allocation % is 0 in the Portfolio. The agent MUST gate by this — we caught a bug where the Excel model was applying DBA effort to all projects regardless of allocation.
3. AGENT CAPABILITIES
3a. Core (MVP)
Portfolio Status | Answer: "What's the status of Highest projects?" "Which projects are stuck?" "How many projects does Tom lead?" Grounded in live Excel data.
Capacity Analysis | Calculate real-time utilization by role. Weekly supply = headcount × 32. Weekly demand = Σ(Est.Hours × Role% × SDLC Phase Effort%) / duration. Thresholds: <80% green, 80-99% yellow, ≥100% red.
What-If Scenarios | "What if we add a 400-hr project?" → adds demand, identifies overloaded weeks, generates 2-4 mitigation options with specific numbers.
Schedule Optimization | Sort by priority. Place projects on timeline. If any role exceeds 85%, shift lower-priority projects forward until it fits. Never shift Highest/High. Output: recommended dates + shift amounts.
Trade-Off Options | When constrained, generate 2-4 options: (A) delay specific projects, (B) add headcount + cost est., (C) reduce scope, (D) accept short overload. Rank by recommendation.
Change Detection | Compare current Excel to last snapshot. Report: new projects, status changes, % complete changes, date changes. Proactive at start of each session.
3b. Stretch (Phase 1.5)
Board Summary | Generate plain-English executive summary: active projects, utilization, top risks, decisions made. Write to Excel sheet.
Proactive Alerts | Teams/Slack notification when: role > 90%, project stuck > 2 weeks, end date passed with < 90% complete.
Trend Analysis | "How has Developer utilization trended over 8 weeks?" Requires storing weekly snapshots.
4. TECHNICAL ARCHITECTURE
Runtime | Python 3.11+, long-lived process (server, Azure Function, or local PC)
AI Model | Claude Sonnet 4 (claude-sonnet-4-20250514) via Anthropic API with tool-use
Optimization | Google OR-Tools (free, handles constraint programming). Objective: minimize total delay, constraints: all roles ≤ 85% utilization, priority hierarchy respected.
Memory | SQLite database. Tables: portfolio_snapshots (weekly state), decisions (approved actions + reasoning), agent_state (preferences, last run date).
Chat Interface | Option A: Streamlit web app (fastest to build, ~50 lines). Option B: Teams bot (best adoption, needs Azure AD setup).
Excel Access | openpyxl for direct file read/write. NEVER overwrite Portfolio or Team Roster without explicit user confirmation. Write only to output sheets.
5. SYSTEM PROMPT (Draft)
System Prompt | You are the ETE IT PMO Resource Planning Agent. You help the PMO team make data-driven resource allocation decisions. RULES: • Highest priority = immovable. Never delay. • High priority = minimal flex (≤2 weeks). • Medium/Low = flexible. Delay these first. • Target utilization: 85%. Red ≥100% must be resolved. • Demand = Est.Hours × Role% × SDLC Phase Effort% / Duration. Only if Role% > 0. • Always provide 2-4 concrete options with specific numbers. • Never overwrite source sheets without confirmation. • Lead with the answer, then supporting detail. • Cite specific numbers: "Developer at 106%" not "Developer is overloaded".
6. IMPLEMENTATION PLAN
Week 1: Foundation | Day 1-2: Excel Connector (read_portfolio, read_roster, read_assumptions) Day 3-4: Claude API + tool-use integration + system prompt Day 5: Memory store (SQLite, save/load/compare snapshots)
Week 2: Intelligence | Day 6-8: OR-Tools optimization engine (constraint solver for scheduling) Day 9-10: What-if scenario engine (add project, lose resource, shift dates)
Week 3: Interface | Day 11-12: Streamlit chat UI or Teams bot Day 13-14: End-to-end testing with real data (5 core scenarios) Day 15: Deployment + team training
7. SUCCESS CRITERIA
Accuracy | Utilization calculations match Excel within 1% tolerance.
Speed | All queries answered in <10 seconds (Excel read + Claude API + optimization).
Memory | Correctly identifies changes between sessions unprompted.
Optimization | All roles ≤85% in leveled schedule. No Highest project delayed. Total delay minimized.
Adoption | PMO lead uses agent ≥3x/week within 2 weeks of deployment.
Board Ready | Agent-generated summary needs <5 min of editing for board deck.
8. RISKS & MITIGATIONS
Stale Data | If Excel not saved/synced, agent reads old data. Mitigation: show "Data as of: [timestamp]" in every response.
AI Hallucination | Agent could generate plausible wrong numbers. Mitigation: every claim must trace to a tool call with cited source data.
Accidental Overwrite | Agent writes to wrong cells. Mitigation: hard-code whitelist of writable sheets (RM_Gantt, Board_Summary). Require confirmation.
Impractical Schedule | Algorithm shifts project 16 weeks. Mitigation: cap max shift by priority (Highest:0, High:2, Medium:8, Low:16 weeks).
Adoption Risk | Team doesn't use it. Mitigation: start with PMO lead only, prove value, then expand. Excel stays primary interface.