## Dashboard
ETE IT PMO — Resource & Project Management Dashboard
| TEAM SIZE |  |  | WEEKLY CAPACITY |  |  | TEAM UTILIZATION |  |  | starting / available time | use 10/10/80
| 23 |  |  | 438.74 |  |  | 10.52% |  |  | allocation of available time: allocate 10% allocation for admin, 15% for break/fix, 75% for projects - 40 hour week
| Total resources |  |  | Net project hrs/wk |  |  | Across active weeks
this gives us our model of resource availability; meetings should be focused on the project and project plan
RESOURCE CAPACITY OVERVIEW
| Team | Headcount | Weekly Hrs | Support Reserve | Net Capacity | Avg Allocated | Available | Utilization |  | for ba's / sdlc: 75% of effort on a project (of the 10%) is in discovery and planning
| Synnergie (ERP) | 8 | 280 | 105 | 175 | 13.5 | 161.5 | 7.714% |  | rest of their time is the other / remainder
| Systems Applications | 4 | 100 | 31.25 | 68.75 | 20.8696 | 47.8804 | 30.36% |  | technical side (discovery/ planning) - 5-%, design is 50-75%, build is 75%-80%
| Business Analysts | 4 | 145 | 66 | 79 | 8.7675 | 70.2325 | 11.1%
| Infrastructure | 3 | 120 | 72 | 48 | 0 | 48 | 0% |  | no more than 3 projects per person at a time
| WMS | 1 | 35 | 21 | 14 | 0 | 14 | 0%
| PMO | 3 | 102 | 48.01 | 53.99 | 3 | 50.99 | 5.557% |  | once developers are done, then ba's go from 10-15% to 25%-30%
| TOTAL | 23 | 782 | 343.26 | 438.74 | 46.137 | 392.603 | 10.52%
need multiple dimensions in the model for how we visualize the projects - some might be businer in some phases
PROJECT STATUS SUMMARY
| Category | Total | Complete | In Progress | Not Started | Needs Help | Needs Spec | Postponed | % Complete | 32 hours, divide by 2, 16 hours free for something else - gives availability of who's red and and not; assign people to rosters
| Project Portfolio | 37 | 16 | 4 | 2 | 0 | 7 | 9 | 43.24%
can be assigned to more than 2-3 projeects start/ end at different times
identify how much work is required per resource type per week; maybe as an ex: 300 per ba: have more demand than supply
[6 empty] | must have staggerred start dates based on resource capacity adn avail |  |  |  | heatmap to change when we add an additional person b/c more resources
[6 empty] | dates, groups, resource capacity, etc.. amount of work does not change |  |  |  | do we have all the right people or not
but as we move dates it should change heatmap b/c of availability

## Team Roster
ETE IT PMO — Team Roster & Capacity
Resource | Role | Team | Vendor | Resource Classification | Rate/Hour | Weekly Hrs Available | Support Reserve % | Project Capacity % | Support Reserve (hrs/wk) | Project Capacity (hrs/wk)
Ajay Kumar | Functional | ERP | Synnergie | MSA | 65 | 35 | 40% | 60% | 14 | 21
Ravindra Reddy | Technical | ERP | Synnergie | MSA | 65 | 35 | 40% | 60% | 14 | 21
Vishnu Premen | Technical | ERP | Synnergie | T&M | 65 | 35 | 40% | 60% | 14 | 21
Deepak Gudwani | Functional | ERP | Synnergie | T&M | 65 | 35 | 40% | 60% | 14 | 21
Sangamesh Koti | Technical | ERP | Synnergie | T&M | 65 | 35 | 0% | 100% | 0 | 35
Bhavya Reddy | Technical | ERP | Synnergie | T&M | 65 | 35 | 0% | 100% | 0 | 35
Sarath Yeturu | Technical | ERP | Synnergie | MSA | 65 | 35 | 60% | 40% | 21 | 14
Vinod Bollepally | DBA | ERP | Synnergie | MSA | 65 | 35 | 80% | 20% | 28 | 7
Jim Young | Business Analyst | Business Analysts | ETE | Internal | 65 | 40 | 60% | 40% | 24 | 16
Alex Young | Developer | Systems Applications | ETE | Internal | 65 | 25 | 50% | 50% | 12.5 | 12.5
Nick Smith | Developer | Systems Applications | ETE | Internal | 65 | 25 | 40% | 60% | 10 | 15
Colin Olson | Developer | Systems Applications | ETE | Internal | 65 | 25 | 10% | 90% | 2.5 | 22.5
Jonathon Gonzalez | Developer | Systems Applications | ETE | Internal | 65 | 25 | 25% | 75% | 6.25 | 18.75
Audrey Debaere | Business Analyst | Business Analysts | ETE | Internal | 65 | 35 | 50% | 50% | 17.5 | 17.5
Cristian Varelas | Business Analyst | Business Analysts | ETE | Internal | 65 | 35 | 20% | 80% | 7 | 28
Ryan Picado | Business Analyst | Business Analysts | ETE | Internal | 65 | 35 | 50% | 50% | 17.5 | 17.5
Emily Fridley | Project Manager | PMO | ETE | Internal | 65 | 35 | 50% | 50% | 17.5 | 17.5
Brett Anderson | Project Manager | PMO | ETE | Internal | 65 | 35 | 25% | 75% | 8.75 | 26.25
Bettina Kotico | Project Manager | PMO | Kayana | T&M | 65 | 32 | 68% | 32% | 21.76 | 10.24
Donna Wiedemeier | WMS Consultant | WMS | Watermark | T&M | 65 | 35 | 60% | 40% | 21 | 14
Justin Senour | Infrastructure | Infrastructure | ETE | Internal | 65 | 40 | 60% | 40% | 24 | 16
Michael House | Infrastructure | Infrastructure | ETE | Internal | 65 | 40 | 60% | 40% | 24 | 16
Andrew Shaefer | Infrastructure | Infrastructure | ETE | Internal | 65 | 40 | 60% | 40% | 24 | 16
TOTALS | [5 empty] | 782 | 43.9% | 56.1% | 343.26 | 438.74

## Project Portfolio
ETE IT PMO — Project Portfolio
ID | Project Name | Type | Business Portfolio | Sponsor/Leader | Project Health | % Complete | Priority | Start Date | Est. End Date | Actual/Updated End | Team | PM | BA | Functional | Technical | T-Shirt Size | Est. Hours | Est. Cost Range | BA % | Functional % | Technical % | Developer % | Infrastructure % | DBA % | PM % | WMS % | Notes | Sort Order
ETE-83 | Customer Master Data Cleanup | Key Initiative | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 15% | High | 2025-10-14 | 2026-06-01 |  | Systems Applications |  | Jim Young |  |  | XXL: > 640 Hours | 1480 | 96200 | 10% | [7 empty] | Completed Q1 | 1
ETE-48 | System Connection Syteline-VKS | Key Initiative | Engineering | Ray Trumble | 🟢 ON TRACK | 10% | High | 2026-02-15 | 2026-06-30 |  | Synnergie | Emily Fridley |  |  |  | L: 160-320 Hours | 240 | 15600 | 10% | [5 empty] | 25% |  |  | 1
ETE-68 | Catalog API Rust2Python | Key Initiative | Information Technology | Jim Koscielniak | 🟢 ON TRACK | 13% | High | 2025-11-17 | 2026-04-24 |  | Systems Applications |  | Cristian Varelas |  | Colin Olson | XXL: > 640 Hours | 640 | 41600 | 10% |  |  | 75% | [5 empty] | 1
ETE-43 | Data Security - Microsoft Purview | Key Initiative | Information Technology | Jim Koscielniak | 🟢 ON TRACK | 0% | High | 2026-02-02 | 2026-06-30 |  | Infrastructure | [5 empty] | 0 | 0 | 10% | [8 empty] | 1
ETE-19 | Changes to AR Aging Report | Enhancement | Finance | Tom Newell | 🟢 ON TRACK | 0% | High | 2026-02-23 | 2026-04-17 |  | Synnergie |  | Audrey Debaere | Ajay Kumar | Bhavya Reddy | M: 80-160 Hours | 120 | 7800 | 10% | 25% | 65% | [6 empty] | 1
ETE-49 | Marketing: STE Rewards Tier | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 0% | Medium |  |  |  | Systems Applications |  | Cristian Varelas |  |  | L: 160-320 Hours | 240 | 15600 | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0% |  | 1
ETE-7 | Outsourced Unit Core Accounting | Enhancement | Finance | Tom Newell | 📋 NEEDS FUNCTIONAL SPEC | 0% | Medium |  |  |  | Synnergie |  | Audrey Debaere |  |  | XXL: > 640 Hours | 640 | 41600 | 10% | 25% | 65% | 0% | 0% | 0% | 0% | 0% | 8-9 month project | 1
ETE-52 | SWIMS/Syteline Reporting | Enhancement | Supply Chain | Jon Besherse | 📋 NEEDS TECHNICAL SPEC | 0% | Medium |  |  |  | Systems Applications |  | Ryan Picado |  |  | S: < 80 Hours | 40 | 2600 | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0% |  | 1
ETE-16 | Partial Pay w/ CC from WMERP | Enhancement | Finance | Tom Newell | ⚪ NOT STARTED | 0% | Medium |  |  |  | Synnergie |  |  |  |  | M: 80-160 Hours | 120 | 7800 | 10% | 25% | 65% | 0% | 0% | 0% | 0% | 0% |  | 1
ETE-37 | Magic Search in BuyETE | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS TECHNICAL SPEC | 0% | Highest |  |  |  | Systems Applications |  | Cristian Varelas |  |  | S: < 80 Hours | 40 | 2600 | 10% | 25% | 0% | 65% | 0% | 0% | 0% | 0% |  | 1
ETE-97 | Standard Order Process Notifications | Enhancement | Sales & Distribution | Tom Vierling | ⚪ NOT STARTED | 0% | Highest |  |  |  | Systems Applications | [5 empty] | 200 | 13000 | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0% |  | 1
ETE-100 | ATSG Expired Members Self-Payment | Enhancement | Sales & Distribution | Tom Vierling | 📋 NEEDS FUNCTIONAL SPEC | 0% | Medium |  |  |  | Systems Applications | [5 empty] | 200 | 13000 | 10% | 0% | 0% | 75% | 0% | 0% | 0% | 0% |  | 1
ETE-124 | Clean Up Return Loads | Enhancement | Finance | Tom Newell | 📋 NEEDS TECHNICAL SPEC | 0% | Highest |  |  |  | Synnergie | [5 empty] | 200 | 13000 | 10% | 25% | 75% | 0% | 0% | 0% | 0% | 0% |  | 1
1
ETE-58 | Transfer Order Moved Items to Transit Location | Enhancement | Finance | Jim Young | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-51 | RMA Credit Memo on Ghost Check-In | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-59 | Reconcile BridgePay CC Transactions | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-60 | EDI Payments Not Posting on Background | Enhancement | Finance | Tom Newell | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-61 | Accum Deposits Received Field | Bug | Finance | Tom Newell | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-86 | Allow TCM Core Receiving to Post | Enhancement | Engineering | Ray Trumble | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-34 | Salesforce BDR Application & Process Implementation | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-35 | BuyETE Ability for Customers to Save Quotes | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0% | [21 empty] | 2
ETE-33 | EDI 3PL Locations | Enhancement | Sales & Distribution | Tom Vierling | ⏸️ POSTPONED | 0% | High |  |  |  | Systems Applications |  | Jim Young |  |  | M: 80-160 Hours | 120 | [10 empty] | 2
ETE-67 | Avalara Tax Issues | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | Highest | 2026-02-04 | 2026-02-27 |  | Synnergie |  | Audrey Debaere | Deepak Gudwani | Sangamesh Koti | M: 80-160 Hours | 120 | 7800 | 10% | 25% | 75% | [6 empty] | 3
ETE-14 | Installed Return RMA Type | Enhancement | Supply Chain | Jon Besherse | ✅ COMPLETE | 100% | Highest | 2026-03-02 | 2026-03-20 |  | Synnergie |  | Audrey Debaere |  |  | M: 80-160 Hours | 120 | 7800 | 10% | 25% | 65% | [6 empty] | 3
ETE-70 | Nutanix (Replace VMware) | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | Highest | 2025-12-01 | 2026-03-21 |  | Infrastructure |  |  |  | Michael House |  | 120 | 7800 | 10% |  |  |  | 50% |  |  |  |  | 3
ETE-65 | Rebuild Vendor Portal | Enhancement | Sales & Distribution | Tom Vierling | ✅ COMPLETE | 100% | High | 2025-10-27 | 2026-01-09 | 2026-02-15 | Systems Applications |  | Jim Young |  | Jonathon Gonzalez | S: < 80 Hours | 60 | 11895 | [9 empty] | 3
ETE-69 | Core Plan Optimization | Key Initiative | Supply Chain | Jon Besherse | ✅ COMPLETE | 100% | High | 2025-11-12 | 2026-01-23 | 2026-01-23 | Synnergie |  | Audrey Debaere |  | Ravindra Reddy | L: 160-320 Hours | 360 | 16120 | [9 empty] | 3
ETE-31 | Restocking Fees Added to RMA Credit Memo | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | High | 2024-12-22 | 2026-02-06 | 2026-02-28 | Synnergie |  | Audrey Debaere |  | Bhavya Reddy | L: 160-320 Hours | 310 | 1625 | [9 empty] | 3
ETE-45 | VB Bin Printer Integration | Enhancement | Engineering | Ray Trumble | ✅ COMPLETE | 100% | High | 2025-10-20 | 2026-02-20 | 2026-02-20 | Synnergie |  | Cristian Varelas |  | Sangamesh Koti | M: 80-160 Hours | 160 | 260 | [9 empty] | 3
ETE-42 | Gear Screen - Improved Production Oversight | Key Initiative | Production | Ari Rosengarten | ✅ COMPLETE | 100% | High | 2026-01-12 | 2026-02-05 | 2026-02-28 | Synnergie |  | Cristian Varelas |  | Vishnu Premen | M: 80-160 Hours | 120 | [9 empty] | NAPA not ready | 3
ETE-72 | Fortigate ZTNA - EMS Setup | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | High | 2025-12-12 | 2025-12-31 | 2026-02-27 | Infrastructure |  |  |  | Justin Senour |  | 0 | [10 empty] | 3
ETE-71 | One Drive Migration | Key Initiative | Information Technology | Jim Koscielniak | ✅ COMPLETE | 100% | High | 2025-12-22 | 2026-02-06 | 2026-02-15 | Infrastructure |  |  |  | Michael House |  | 0 | [10 empty] | 3
ETE-87 | Production Dashboard | Enhancement | Production | Ari Rosengarten | ✅ COMPLETE | 100% | High |  |  |  | Systems Applications |  |  |  |  | S: < 80 Hours | 40 | [10 empty] | 3
ETE-88 | Return Load Phase 2 | Key Initiative | Finance | Tom Newell | ✅ COMPLETE | 100% | High | 2025-10-27 | 2025-12-29 | 2026-01-09 | Synnergie |  | Audrey Debaere |  | Sangamesh Koti |  | 320 | [10 empty] | 3
ETE-73 | Teal Parts Daily Inventory Feed | Enhancement | Sales & Distribution | Tom Vierling | ✅ COMPLETE | 100% | Highest |  |  |  | Systems Applications |  | Cristian Varelas |  |  | S: < 80 Hours | 40 | [10 empty] | 3
ETE-10 | Upload Utility for Planning Fields | Enhancement | Supply Chain | Tom Green | ✅ COMPLETE | 10% | Highest |  |  |  | Synnergie |  | Audrey Debaere |  |  | S: < 80 Hours | 80 | [10 empty] | 3
ETE-32 | Form: Cash App SQL Fix | Enhancement | Finance | Tom Newell | ✅ COMPLETE | 100% | High |  |  |  | Synnergie |  | Audrey Debaere |  |  | L: 160-320 Hours | 320 | [10 empty] | 3
ETE-76 | FedEx Web Services API | Enhancement | Information Technology | Jim Koscielniak | ✅ COMPLETE | 0% | High | 2026-03-03 | 2026-03-13 |  | Systems Applications |  | Jim Young |  | Alex Young | S: < 80 Hours | 40 | [10 empty] | 3

## Project Timeline
ETE IT PMO — Project Timeline (Gantt View)
Auto-populated from Project Portfolio ¦ Non-complete projects only ¦ Red line = current week
[6 empty] | January 2026 |  |  |  | February 2026 |  |  |  | March 2026 |  |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  |  | July 2026 |  |  |  | August 2026 |  |  |  |  | September 2026 |  |  |  | October 2026 |  |  |  | November 2026 |  |  |  |  | December 2026
# | Project ID | Project Name | Project Health | Start | End | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
1 | ETE-19 | Changes to AR Aging Report | 🟢 ON TRACK | 2026-02-23 | 2026-04-17 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | ETE-68 | Catalog API Rust2Python | 🟢 ON TRACK | 2025-11-17 | 2026-04-24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | ETE-83 | Customer Master Data Cleanup | 📋 NEEDS TECHNICAL SPEC | 2025-10-14 | 2026-06-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | ETE-48 | System Connection Syteline-VKS | 🟢 ON TRACK | 2026-02-15 | 2026-06-30 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | ETE-43 | Data Security - Microsoft Purview | 🟢 ON TRACK | 2026-02-02 | 2026-06-30 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | ETE-49 | Marketing: STE Rewards Tier | 📋 NEEDS TECHNICAL SPEC
7 | ETE-7 | Outsourced Unit Core Accounting | 📋 NEEDS FUNCTIONAL SPEC
8 | ETE-52 | SWIMS/Syteline Reporting | 📋 NEEDS TECHNICAL SPEC
9 | ETE-16 | Partial Pay w/ CC from WMERP | ⚪ NOT STARTED
10 | ETE-37 | Magic Search in BuyETE | 📋 NEEDS TECHNICAL SPEC
11 | ETE-97 | Standard Order Process Notifications | ⚪ NOT STARTED
12 | ETE-100 | ATSG Expired Members Self-Payment | 📋 NEEDS FUNCTIONAL SPEC
13 | ETE-124 | Clean Up Return Loads | 📋 NEEDS TECHNICAL SPEC

## RM_Guide
ETE IT PMO — Resource Model Guide
A plain-English explanation of how the Resource Model works, what each sheet does, and how to use it.
THE BIG PICTURE
What is this? | A set of 4 connected sheets that answer: "Do we have enough people for all these projects, and when will we be in trouble?"
Why does it exist? | The Portfolio shows WHAT projects we have. The Resource Model shows WHETHER we can actually staff them — and when bottlenecks will hit.
Who should use it? | PMO leads for weekly planning, resource decisions, and "what if" scenario testing (hiring, project delays, reprioritization).
How do the sheets connect? | RM_Assumptions (rules) → RM_Demand (how much work) → RM_SupplyVsDemand (big picture) → RM_WeeklyHeatmap (when exactly).
What are the blue cells? | Any cell with a blue/light blue background is an INPUT you can change. These are your scenario levers — adjust them and the model recalculates automatically.
SHEET-BY-SHEET EXPLANATION
📋 RM_Assumptions | "What are our rules?" — This is the control panel for the whole model.
Time Allocation (rows 6-12) | Each person works 40 hrs/week, but not all of it goes to projects. Admin (10%) and Break/Fix support (10%) eat into that, leaving 80% = 32 hrs/week for project work. You can change these percentages.
SDLC Phase Weights (row 16) | A project isn't evenly spread. It's 10% Discovery → 10% Planning → 15% Design → 30% Build → 20% Test → 15% Deploy. These must add to 100%. Change them to match your actual project lifecycle.
Role Effort by Phase (rows 21-28) | THIS IS THE KEY INSIGHT. A DBA isn't equally busy throughout a project. They barely touch Discovery (5%) but are heavily loaded in Build (30%). A BA is the opposite — 30% in Discovery, only 10% in Build. These percentages drive the weekly demand spikes in the heatmap.
Team Supply (rows 30-38) | Auto-counts headcount and hours from the Team Roster. You don't edit these — they update when Team Roster changes.
📊 RM_Demand | "How much work is coming?" — Calculates total demand from active projects.
Active Projects (rows 6-18) | Automatically pulls all non-complete, non-postponed projects from the Portfolio. You don't edit these rows — they update when Portfolio changes.
Total Demand by Role (rows 24-30) | For each role, adds up: (Project Est. Hours × Role Allocation %) across all active projects. Shows you the total hours each role needs to deliver.
Project × Role Detail (rows 36-48) | A breakdown showing exactly how many hours each project needs from each role. Useful for seeing which projects are driving the most demand.
⚖️ RM_SupplyVsDemand | "Are we OK overall?" — A summary scorecard comparing supply to demand.
Capacity Scorecard (rows 5-7) | The headline numbers: Total Supply hrs/wk, Total Demand hrs/wk, Net Gap (+ means surplus, - means deficit), and Overall Utilization %.
By Role (rows 11-17) | Same comparison broken out by role. Color-coded: green = fine, yellow = tight, red = over capacity. This tells you WHERE the problem is.
Scenario Notes (rows 31-37) | A free-text area for documenting assumptions, decisions, and scenario notes from planning sessions.
🗓️ RM_WeeklyHeatmap | "WHEN are we in trouble?" — The action sheet you use in weekly planning.
Headcount Adjusters (rows 6-12) | Type a number in the blue "Add/Remove" cells to simulate hiring or losing staff. Type 1 next to DBA to test "what if we hire another DBA?" Type -1 to test losing someone. The heatmap recalculates instantly.
Project Timelines (rows 17-29) | Shows each active project's start/end dates (blue = editable). Change a date to test "what if we delay ETE-43 by a month?" or "what if we start ETE-49 sooner?" The heatmap recalculates.
The Heatmap (rows 34-40) | The payoff. Each cell shows utilization % for one role in one week. Green (<80%) = fine. Yellow (80-99%) = getting tight. Red (100%+) = overloaded, need to act. Demand shifts week-to-week because the model knows which SDLC phase each project is in.
HOW TO RUN SCENARIOS
"What if we hire another DBA?" | Go to RM_WeeklyHeatmap → cell C11 (DBA Add/Remove) → type 1. The DBA row in the heatmap will drop from red to green. If it works, you've justified the hire.
"What if we delay a project?" | Go to RM_WeeklyHeatmap → find the project in rows 17-29 → change its Start Date (column D) or End Date (column E). The heatmap will shift that project's demand to different weeks.
"What if a project takes longer?" | Push the End Date further out. The same total hours get spread over more weeks, so weekly demand drops — but it stays on the heatmap longer.
"What if we change how much BA time a project needs?" | Go to RM_Assumptions → Role Effort by Phase (rows 21-28) → adjust the BA row. This changes how much BA demand every project generates during each phase.
"What if we shift more time to admin?" | Go to RM_Assumptions → Time Allocation (rows 7-9) → increase Admin %, decrease Project %. Everyone's available project hours shrink, so utilization goes up across the board.
Reset everything | Set all Headcount Adjusters back to 0. The project dates will revert to Portfolio defaults on their own (they pull from Portfolio when not overridden).
READING THE HEATMAP COLORS
🟢 Green (under 80%) | This role has capacity. No action needed.
🟡 Yellow (80-99%) | At risk. A short burst of yellow (1-2 weeks) is OK — people can push through. But sustained yellow over 3+ weeks means you're running tight and any surprise will tip into red.
🔴 Red (100% or higher) | Over capacity. This role physically can't deliver everything assigned to them. Something has to give: hire more, delay a project, or reassign work. The higher the %, the worse it is (183% means you'd need almost 2x the people).
All zeros (0%) | Either no projects are active that week, or no projects need that role. Check if project dates are set correctly in the timeline section.
IMPORTANT NOTES
Projects with no dates | If a project in the Portfolio has no Start/End date, the heatmap defaults it to starting today with a 12-week duration. Once real dates are added to the Portfolio, it picks them up automatically.
Completed/Postponed projects | These are automatically excluded from all demand calculations. You don't need to remove them.
Phase totals over 100% | In RM_Assumptions, the Phase Total row may show >100%. This is correct — it means multiple roles work on the same phase. It's not a distribution (doesn't need to sum to 100%), it's effort intensity per role.
Headcount vs. Team Roster | Base headcount in the heatmap comes from Team Roster via RM_Assumptions. The Adjuster in the heatmap is a temporary "what if" — it doesn't change the actual roster.
Don't edit gray cells | Gray cells contain formulas. If you overwrite them, the model breaks. Only edit blue cells.
📅 RM_Gantt (Resource-Leveled Gantt) | "What's the recommended schedule?" — Shows projects rescheduled to avoid resource overloads.
What it does | Takes all 13 active projects, sorts them by priority (Highest first), and schedules them one by one. If adding a project would push any role over 100% capacity, it pushes that project's start date forward week-by-week until it fits.
Schedule Table (cols A-I) | Shows each project's original dates vs. adjusted dates. The "Shifted" column tells you how many weeks a project was pushed. Yellow-highlighted adjusted dates = the project moved.
Gantt Bars (cols J+) | Color-coded bars: Red = Highest priority, Yellow = High, Blue = Medium. Green ghost bars show where a shifted project was originally scheduled.
Key insight | The DBA is the binding constraint. All 5 Medium projects had to shift because of DBA overload. Highest and High priority projects kept their original dates.
⚠️ Important | This is a one-time snapshot, NOT a live formula. After changing headcount adjusters or project dates in RM_WeeklyHeatmap, ask Claude to regenerate the Gantt to get an updated recommended schedule.

## Capacity Heatmap
ETE IT PMO — Weekly Capacity Heatmap
Overloaded (>100%) | At Capacity (85-100%) | Healthy (50-84%) | Underutilized (<50%)
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26
Resource | Role | Team | Net Capacity (hrs/wk) | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25
Ajay Kumar | Functional | Synnergie | 21 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.86% | 17.86% | 17.86% | 17.86% | 17.86% | 17.86% | 17.86% | 17.86% | 17.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ravindra Reddy | Technical | Synnergie | 21 | bar: 2026-01-01 to 2026-06-25
Vishnu Premen | Technical | Synnergie | 21 | bar: 2026-01-01 to 2026-06-25
Deepak Gudwani | Functional | Synnergie | 21 | bar: 2026-01-01 to 2026-06-25
Sangamesh Koti | Technical | Synnergie | 35 | bar: 2026-01-01 to 2026-06-25
Bhavya Reddy | Technical | Synnergie | 35 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.86% | 27.86% | 27.86% | 27.86% | 27.86% | 27.86% | 27.86% | 27.86% | 27.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sarath Yeturu | Technical | Synnergie | 14 | bar: 2026-01-01 to 2026-06-25
Vinod Bollepally | DBA | Synnergie | 7 | bar: 2026-01-01 to 2026-06-25
Jim Young | Business Analyst | Business Analysts | 16 | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 28.03% | 0% | 0% | 0% | 0%
Alex Young | Developer | Systems Applications | 12.5 | bar: 2026-01-01 to 2026-06-25
Nick Smith | Developer | Systems Applications | 15 | bar: 2026-01-01 to 2026-06-25
Colin Olson | Developer | Systems Applications | 22.5 | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 92.75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Jonathon Gonzalez | Developer | Systems Applications | 18.75 | bar: 2026-01-01 to 2026-06-25
Audrey Debaere | Business Analyst | Business Analysts | 17.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.571% | 8.571% | 8.571% | 8.571% | 8.571% | 8.571% | 8.571% | 8.571% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cristian Varelas | Business Analyst | Business Analysts | 28 | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 9.938% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ryan Picado | Business Analyst | Business Analysts | 17.5 | bar: 2026-01-01 to 2026-06-25
Emily Fridley | Project Manager | PMO | 17.5 | 0% | 0% | 0% | 0% | 0% | 0% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14% | 17.14%
Brett Anderson | Project Manager | PMO | 26.25 | bar: 2026-01-01 to 2026-06-25
Donna Wiedemeier | WMS Consultant | WMS | 14 | bar: 2026-01-01 to 2026-06-25
Justin Senour | Infrastructure | Infrastructure | 16 | bar: 2026-01-01 to 2026-06-25
Michael House | Infrastructure | Infrastructure | 16 | bar: 2026-01-01 to 2026-06-25
Andrew Shaefer | Infrastructure | Infrastructure | 16 | bar: 2026-01-01 to 2026-06-25

## Resource Scheduler
ETE IT PMO — Resource Scheduler
Planning Start Date: | 2026-03-28
WEEKLY AVAILABLE HOURS BY ROLE
Role | # Resources | Total Capacity (hrs/wk) | Avg Support % | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-14 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-11 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-09
Business Analyst | 4 | 79 | 45% | 71.7325 | 71.7325 | 71.7325 | 71.7325 | 71.7325 | 71.7325 | 71.7325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 70.2325 | 71.7325 | 74.5152 | 74.5152 | 74.5152 | 74.5152 | 74.5152 | 79 | 79 | 79 | 79 | 79 | 79
Developer | 4 | 68.75 | 31.25% | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 47.8804 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75 | 68.75
Functional | 2 | 42 | 40% | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
Infrastructure | 3 | 48 | 60% | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
Project Manager | 2 | 43.75 | 47.67% | 43.75 | 43.75 | 43.75 | 43.75 | 43.75 | 43.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 40.75 | 43.75 | 43.75
Technical | 5 | 126 | 28% | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 116.25 | 116.25 | 116.25 | 116.25 | 116.25 | 116.25 | 116.25 | 116.25 | 116.25 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126
DBA | 1 | 7 | 80% | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
WMS Consultant | 1 | 14 | 60% | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
UNSCHEDULED PROJECTS — RESOURCE REQUIREMENTS & SUGGESTED SCHEDULE | bar: 2026-01-01 to 2026-02-26
Project ID | Project Name | Priority | Est. Hours | 2026-01-01: Needs BA?; 2026-01-08: Functional?; 2026-01-15: Technical?; 2026-01-22: Developer?; 2026-01-29: Infrastructure?; 2026-02-05: DBA?; 2026-02-12: Hrs/Wk Needed; 2026-02-19: Earliest Start; 2026-02-26: Projected End
ETE-49 | Marketing: STE Rewards Tier | Medium | 240 | 2026-01-01: Yes; 2026-01-08: No; 2026-01-15: No; 2026-01-22: Yes; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 22.375; 2026-02-19: 2026-03-28; 2026-02-26: 2026-06-15
ETE-7 | Outsourced Unit Core Accounting | Medium | 640 | 2026-01-01: Yes; 2026-01-08: Yes; 2026-01-15: Yes; 2026-01-22: No; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 35.125; 2026-02-19: 2026-03-28; 2026-02-26: 2026-08-03
ETE-52 | SWIMS/Syteline Reporting | Medium | 40 | 2026-01-01: Yes; 2026-01-08: No; 2026-01-15: No; 2026-01-22: Yes; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 22.375; 2026-02-19: 2026-03-28; 2026-02-26: 2026-04-13
ETE-16 | Partial Pay w/ CC from WMERP | Medium | 120 | 2026-01-01: Yes; 2026-01-08: Yes; 2026-01-15: Yes; 2026-01-22: No; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 35.125; 2026-02-19: 2026-03-28; 2026-02-26: 2026-04-27
ETE-37 | Magic Search in BuyETE | Highest | 40 | 2026-01-01: Yes; 2026-01-08: Yes; 2026-01-15: No; 2026-01-22: Yes; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 28.625; 2026-02-19: 2026-03-28; 2026-02-26: 2026-04-06
ETE-97 | Standard Order Process Notifications | Highest | 200 | 2026-01-01: Yes; 2026-01-08: No; 2026-01-15: No; 2026-01-22: Yes; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 22.375; 2026-02-19: 2026-03-28; 2026-02-26: 2026-06-01
ETE-100 | ATSG Expired Members Self-Payment | Medium | 200 | 2026-01-01: Yes; 2026-01-08: No; 2026-01-15: No; 2026-01-22: Yes; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 22.375; 2026-02-19: 2026-03-28; 2026-02-26: 2026-06-01
ETE-124 | Clean Up Return Loads | Highest | 200 | 2026-01-01: Yes; 2026-01-08: Yes; 2026-01-15: Yes; 2026-01-22: No; 2026-01-29: No; 2026-02-05: No; 2026-02-12: 38.625; 2026-02-19: 2026-04-23; 2026-02-26: 2026-06-01
HOW TO USE:
1. In the Project Portfolio tab, fill in Role % columns (T-AA) for each unscheduled project. Hrs/Wk auto-calculates from role % × avg available hours.
2. Role requirements (E-J) and Hrs/Wk Needed (K) auto-populate here from Portfolio. Columns L-M auto-calculate start/end dates.
3. Availability section (top) updates automatically when you add/change project dates in the Project Portfolio
Note on L15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EARLIEST START: Finds the first week (on or after the Planning Start Date in B2) where ALL required roles marked "Yes" have available hours ≥ the Hrs/Wk Needed (column K). Checks up to 6 roles: BA, Functional, Technical, Developer, Infrastructure, DBA. Available hours per role come from the availability section above, which calculates: each person's weekly capacity minus their committed hours from active projects in the Project Portfolio. If no week within the 26-week window has enough capacity for all required roles, the cell will be blank.
Note on M15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PROJECTED END: Calculated as: Earliest Start + (Est. Hours ÷ Hrs/Wk Needed) × 7 days This assumes a steady weekly effort at the rate specified in column I. For example, a 240-hour project at 20 hrs/wk = 12 weeks → end date is 12 weeks after the start date. Note: This is a straight-line estimate. It does not account for capacity fluctuations across weeks — if a resource becomes unavailable mid-project, the actual end date may shift.

## RM_Assumptions
ETE IT PMO — Resource Model Assumptions
All blue inputs are configurable. Change values to run scenarios.
TIME ALLOCATION MODEL
Parameter | Value | Unit | Notes
Base Hours / Week | 40 | hrs | Standard work week
Admin Allocation | 10% | % | Meetings, email, admin tasks
Break/Fix Allocation | 10% | % | Support tickets, break/fix work
Project Allocation | 80% | % | Time available for project work
Available Project Hrs / Person / Wk | 32 | hrs | Base Hrs × Project %
Allocation Check (must = 100%) | 100%
Max Projects / Person | 3 | projects | Constraint: no one on more than 3
SDLC PHASE WEIGHTS
| Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Total
% of Project Effort | 10% | 10% | 15% | 30% | 20% | 15% | 100%
ROLE EFFORT BY SDLC PHASE
% of phase effort per role (rows don't need to sum to 100% — each role works a share of each phase independently)
Role | Discovery | Planning | Design | Build | Test | Deploy/Hypercare | Avg Effort
PM | 10% | 25% | 15% | 20% | 20% | 10% | 17.25%
DBA | 5% | 10% | 30% | 25% | 20% | 10% | 19%
IT Business Analyst/SME | 30% | 20% | 20% | 10% | 15% | 5% | 14.75%
IT Functional Analyst | 20% | 10% | 30% | 15% | 15% | 10% | 16.5%
IT Tech Analyst/Developer | 5% | 10% | 20% | 40% | 15% | 10% | 21%
Developer | 0% | 5% | 10% | 50% | 25% | 10% | 23.5%
Infrastructure | 5% | 10% | 15% | 20% | 15% | 35% | 18%
WMS Consultant | 10% | 15% | 10% | 10% | 5% | 50% | 15.5%
Phase Total (all roles) | 85% | 105% | 150% | 190% | 130% | 140%
SUPPLY: TEAM CAPACITY BY ROLE
Role | Headcount | Hrs/Wk (Gross) | Project Hrs/Wk | Notes
PM | 3 | 102 | 81.6 | Roster role: "Project Manager"
DBA | 1 | 35 | 28 | Roster role: "DBA"
IT Business Analyst/SME | 4 | 145 | 116 | Roster role: "Business Analyst"
IT Functional Analyst | 2 | 70 | 56 | Roster role: "Functional"
IT Tech Analyst/Developer | 5 | 175 | 140 | Roster role: "Technical"
Developer | 4 | 100 | 80 | Roster role: "Developer"
Infrastructure | 3 | 120 | 96 | Roster role: "Infrastructure"
WMS Consultant | 1 | 35 | 28 | Roster role: "WMS Consultant"
TOTAL | 23 | 782 | 625.6

## RM_Demand
ETE IT PMO — Resource Demand by Role
Demand calculated from Project Portfolio using RM_Assumptions. All formulas reference configurable inputs.
ACTIVE PROJECTS — DEMAND INPUTS
Project ID | Project Name | Status | Priority | Est. Hours | BA % | Functional % | Technical % | Developer % | Infrastructure % | DBA % | PM %
ETE-83 | Customer Master Data Cleanup | 📋 NEEDS TECHNICAL SPEC | High | 1480 | 10% | 0% | 0% | 0% | 0% | 0% | 0%
ETE-48 | System Connection Syteline-VKS | 🟢 ON TRACK | High | 240 | 10% | 0% | 0% | 0% | 0% | 0% | 25%
ETE-68 | Catalog API Rust2Python | 🟢 ON TRACK | High | 640 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-43 | Data Security - Microsoft Purview | 🟢 ON TRACK | High | 0 | 10% | 0% | 0% | 0% | 0% | 0% | 0%
ETE-19 | Changes to AR Aging Report | 🟢 ON TRACK | High | 120 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-49 | Marketing: STE Rewards Tier | 📋 NEEDS TECHNICAL SPEC | Medium | 240 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-7 | Outsourced Unit Core Accounting | 📋 NEEDS FUNCTIONAL SPEC | Medium | 640 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-52 | SWIMS/Syteline Reporting | 📋 NEEDS TECHNICAL SPEC | Medium | 40 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-16 | Partial Pay w/ CC from WMERP | ⚪ NOT STARTED | Medium | 120 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-37 | Magic Search in BuyETE | 📋 NEEDS TECHNICAL SPEC | Highest | 40 | 10% | 25% | 0% | 65% | 0% | 0% | 0%
ETE-97 | Standard Order Process Notifications | ⚪ NOT STARTED | Highest | 200 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-100 | ATSG Expired Members Self-Payment | 📋 NEEDS FUNCTIONAL SPEC | Medium | 200 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-124 | Clean Up Return Loads | 📋 NEEDS TECHNICAL SPEC | Highest | 200 | 10% | 25% | 75% | 0% | 0% | 0% | 0%
TOTAL DEMAND BY ROLE (Hours)
Each project's Est. Hours × role allocation % = total hours that role needs for that project
Role | Total Demand (hrs) | Avg Weeks to Deliver* | Weekly Demand (hrs) | Weekly Supply (hrs) | Weekly Gap | Status
IT Business Analyst/SME | 416 | 12 | 34.6667 | 116 | 81.3333 | ✅ OK
IT Functional Analyst | 280 | 12 | 23.3333 | 56 | 32.6667 | ✅ OK
IT Tech Analyst/Developer | 722 | 12 | 60.1667 | 140 | 79.8333 | ✅ OK
Developer | 1016 | 12 | 84.6667 | 80 | -4.6667 | ⚠️ TIGHT
Infrastructure | 0 | 12 | 0 | 96 | 96 | ✅ OK
DBA | 0 | 12 | 0 | 28 | 28 | ✅ OK
PM | 60 | 12 | 5 | 81.6 | 76.6 | ✅ OK
TOTAL | 2494 |  | 207.8333 | 597.6 | 389.7667
* Avg Weeks to Deliver is configurable per role (blue cells). Adjust based on project pipeline and staggering assumptions.
PROJECT × ROLE DETAIL (Hours per project per role)
Project ID | Est. Hours | BA Hrs | Functional Hrs | Technical Hrs | Developer Hrs | Infra Hrs | DBA Hrs | PM Hrs
ETE-83 | 1480 | 148 | 0 | 0 | 0 | 0 | 0 | 0
ETE-48 | 240 | 24 | 0 | 0 | 0 | 0 | 0 | 60
ETE-68 | 640 | 64 | 0 | 0 | 480 | 0 | 0 | 0
ETE-43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ETE-19 | 120 | 12 | 30 | 78 | 0 | 0 | 0 | 0
ETE-49 | 240 | 24 | 0 | 0 | 180 | 0 | 0 | 0
ETE-7 | 640 | 64 | 160 | 416 | 0 | 0 | 0 | 0
ETE-52 | 40 | 4 | 0 | 0 | 30 | 0 | 0 | 0
ETE-16 | 120 | 12 | 30 | 78 | 0 | 0 | 0 | 0
ETE-37 | 40 | 4 | 10 | 0 | 26 | 0 | 0 | 0
ETE-97 | 200 | 20 | 0 | 0 | 150 | 0 | 0 | 0
ETE-100 | 200 | 20 | 0 | 0 | 150 | 0 | 0 | 0
ETE-124 | 200 | 20 | 50 | 150 | 0 | 0 | 0 | 0
TOTAL | 4160 | 416 | 280 | 722 | 1016 | 0 | 0 | 60

## RM_SupplyVsDemand
ETE IT PMO — Supply vs. Demand Analysis
Side-by-side comparison of available capacity vs. project demand by role. All values flow from RM_Assumptions and RM_Demand.
CAPACITY SCORECARD
TOTAL WEEKLY SUPPLY |  | TOTAL WEEKLY DEMAND |  | NET WEEKLY GAP |  | PROJECT UTILIZATION
625.6 |  | 207.8333 |  | 417.7667 |  | 33.22%
Project hrs/wk |  | Avg hrs/wk needed |  | + surplus / - deficit |  | Demand / Supply
SUPPLY vs. DEMAND BY ROLE
Role | Headcount | Weekly Supply (hrs) | Total Demand (hrs) | Weekly Demand (hrs) | Weekly Gap (hrs) | Utilization % | Status
IT Business Analyst/SME | 4 | 116 | 416 | 34.6667 | 81.3333 | 29.89% | ✅ OK
IT Functional Analyst | 2 | 56 | 280 | 23.3333 | 32.6667 | 41.67% | ✅ OK
IT Tech Analyst/Developer | 5 | 140 | 722 | 60.1667 | 79.8333 | 42.98% | ✅ OK
Developer | 4 | 80 | 1016 | 84.6667 | -4.6667 | 105.8% | ⚠️ NEAR LIMIT
Infrastructure | 3 | 96 | 0 | 0 | 96 | 0% | ✅ OK
DBA | 1 | 28 | 0 | 0 | 28 | 0% | ✅ OK
PM | 3 | 81.6 | 60 | 5 | 76.6 | 6.127% | ✅ OK
TOTAL | 22 | 597.6 | 2494 | 207.8333 | 389.7667 | 34.78%
CAPACITY UTILIZATION BY ROLE (Visual)
Role | Utilization % | Capacity Bar | Interpretation
IT Business Analyst/SME | 29.89% | ██████░░░░░░░░░░░░░░ | 🟢 OK — 81.3 hrs/wk available
IT Functional Analyst | 41.67% | ████████░░░░░░░░░░░░ | 🟢 OK — 32.7 hrs/wk available
IT Tech Analyst/Developer | 42.98% | █████████░░░░░░░░░░░ | 🟢 OK — 79.8 hrs/wk available
Developer | 105.8% | ████████████████████ | ⚠️ OVER — need 4.7 more hrs/wk
Infrastructure | 0% | ░░░░░░░░░░░░░░░░░░░░ | ⚪ No demand
DBA | 0% | ░░░░░░░░░░░░░░░░░░░░ | ⚪ No demand
PM | 6.127% | █░░░░░░░░░░░░░░░░░░░ | 🟢 OK — 76.6 hrs/wk available
SCENARIO PLANNING NOTES
Assumption | Current Value | Impact | How to Change
Time Allocation | 1980-10-10 | Increasing project % gives more capacity per person | RM_Assumptions B7:B9
Avg Weeks to Deliver | 12 wks (all roles) | Fewer weeks = higher weekly demand peak | RM_Demand C24:C30
Role Effort by Phase | See RM_Assumptions | Shifting effort between phases changes peak demand timing | RM_Assumptions B21:G28
Headcount | 23 total | Adding headcount to bottleneck roles directly increases supply | Team Roster (source)
Project Mix | 13 active projects | Completing or postponing projects reduces demand | Project Portfolio status

## RM_WeeklyHeatmap
ETE IT PMO — Weekly Resource Heatmap
Change blue cells to run scenarios: adjust headcount, shift project dates, see impact on weekly utilization by role.
SCENARIO: HEADCOUNT ADJUSTERS
Role | Base Headcount | Add/Remove | Scenario Headcount | Hrs/Person/Wk | Scenario Supply/Wk
IT Business Analyst/SME | 4 | 0 | 4 | 32 | 128
IT Functional Analyst | 2 | 0 | 2 | 32 | 64
IT Tech Analyst/Developer | 5 | 0 | 5 | 32 | 160
Developer | 4 | 0 | 4 | 32 | 128
Infrastructure | 3 | 0 | 3 | 32 | 96
DBA | 1 | 0 | 1 | 32 | 32
PM | 3 | 0 | 3 | 32 | 96
TOTAL | 22 | 0 | 22 |  | 704
SCENARIO: PROJECT TIMELINES
Project ID | Project Name | Est. Hours | Scenario Start | Scenario End | Duration (wks) | BA % | Func % | Tech % | Dev % | Infra % | DBA % | PM %
ETE-83 | Customer Master Data Cleanup | 1480 | 2025-10-14 | 2026-06-01 | 32.8571 | 10% | 0% | 0% | 0% | 0% | 0% | 0%
ETE-48 | System Connection Syteline-VKS | 240 | 2026-02-15 | 2026-06-30 | 19.2857 | 10% | 0% | 0% | 0% | 0% | 0% | 25%
ETE-68 | Catalog API Rust2Python | 640 | 2025-11-17 | 2026-04-24 | 22.5714 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-43 | Data Security - Microsoft Purview | 0 | 2026-02-02 | 2026-06-30 | 21.1429 | 10% | 0% | 0% | 0% | 0% | 0% | 0%
ETE-19 | Changes to AR Aging Report | 120 | 2026-02-23 | 2026-04-17 | 7.5714 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-49 | Marketing: STE Rewards Tier | 240 | 2026-03-28 | 2026-06-20 | 12 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-7 | Outsourced Unit Core Accounting | 640 | 2026-03-28 | 2026-06-20 | 12 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-52 | SWIMS/Syteline Reporting | 40 | 2026-03-28 | 2026-06-20 | 12 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-16 | Partial Pay w/ CC from WMERP | 120 | 2026-03-28 | 2026-06-20 | 12 | 10% | 25% | 65% | 0% | 0% | 0% | 0%
ETE-37 | Magic Search in BuyETE | 40 | 2026-03-28 | 2026-06-20 | 12 | 10% | 25% | 0% | 65% | 0% | 0% | 0%
ETE-97 | Standard Order Process Notifications | 200 | 2026-03-28 | 2026-06-20 | 12 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-100 | ATSG Expired Members Self-Payment | 200 | 2026-03-28 | 2026-06-20 | 12 | 10% | 0% | 0% | 75% | 0% | 0% | 0%
ETE-124 | Clean Up Return Loads | 200 | 2026-03-28 | 2026-06-20 | 12 | 10% | 25% | 75% | 0% | 0% | 0% | 0%
WEEKLY UTILIZATION HEATMAP
Role \ Week Starting → | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06
IT Business Analyst/SME | 1.178% | 4.522% | 3.109% | 2.985% | 2.923% | 1.719% | 1.367% | 1.367% | 1.416% | 1.962% | 1.786% | 0.6927% | 0.5955% | 0.04861% | 0.04861% | 0%
IT Functional Analyst | 0.9287% | 7.439% | 4.184% | 3.874% | 9.766% | 4.883% | 4.883% | 4.883% | 4.883% | 4.883% | 4.883% | 3.255% | 3.255% | 0% | 0% | 0%
IT Tech Analyst/Developer | 2.575% | 2.643% | 4.32% | 3.998% | 6.708% | 13.42% | 13.42% | 13.42% | 13.42% | 5.031% | 5.031% | 3.354% | 3.354% | 0% | 0% | 0%
Developer | 4.153% | 4.153% | 3.406% | 3.406% | 5.151% | 17.45% | 17.45% | 17.45% | 17.45% | 8.724% | 8.724% | 3.49% | 3.49% | 0% | 0% | 0%
Infrastructure | bar: 2026-03-23 to 2026-07-06
DBA | bar: 2026-03-23 to 2026-07-06
PM | 0.4861% | 0.4861% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.6481% | 0.3241% | 0.3241% | 0.3241% | 0%
LEGEND: 🟢 Green (<80%) = OK ¦ 🟡 Yellow (80-99%) = At Risk ¦ 🔴 Red (≥100%) = Over Capacity
HOW TO USE: Change Add/Remove (C6:C12) to test adding staff. Change Scenario Start/End dates (D17:E29) to shift projects.
PHASE BOUNDARIES (Helper — calculates which SDLC phase each project is in each week)
Phase | 2026-03-23: Discovery; 2026-03-30: Planning; 2026-04-06: Design; 2026-04-13: Build; 2026-04-20: Test; 2026-04-27: Deploy
Weight | 2026-03-23: 10%; 2026-03-30: 10%; 2026-04-06: 15%; 2026-04-13: 30%; 2026-04-20: 20%; 2026-04-27: 15%
Cumulative | 2026-03-23: 10%; 2026-03-30: 20%; 2026-04-06: 35%; 2026-04-13: 65%; 2026-04-20: 85%; 2026-04-27: 100%
Formulas:
Scenario Headcount = IF(IFERROR(INDEX('Project Portfolio'!I$4:I42,MATCH([Role],'Project Portfolio'!A$4:A42,0)),0)=0,IF([Role]="","",TODAY()),INDEX('Project Portfolio'!I$4:I42,MATCH([Role],'Project Portfolio'!A$4:A42,0)))
Hrs/Person/Wk = IF(IFERROR(INDEX('Project Portfolio'!J$4:J42,MATCH([Role],'Project Portfolio'!A$4:A42,0)),0)=0,IF([Role]="","",[Scenario Headcount]+84),INDEX('Project Portfolio'!J$4:J42,MATCH([Role],'Project Portfolio'!A$4:A42,0)))

## RM_Gantt
mpl
Projects scheduled by priority. Highest/High go first; Medium shifts as needed to keep all roles ≤100%.
⚠️ Recommended schedule — regenerate after changing headcount or dates in RM_WeeklyHeatmap.
ID | Project Name | Priority | Est Hrs | Orig Start | Orig End | Adj Start | Adj End | Shifted | 2025-10-14 | 2025-10-21 | 2025-10-28 | 2025-11-04 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 2026-06-23 | 2026-06-30 | 2026-07-07 | 2026-07-14 | 2026-07-21 | 2026-07-28 | 2026-08-04 | 2026-08-11 | 2026-08-18
ETE-37 | Magic Search in BuyETE | Highest | 40 | 2026-03-27 | 2026-06-19 | 2026-03-27 | 2026-06-19 | — | [24 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-97 | Std Order Process Notifs | Highest | 200 | 2026-03-27 | 2026-06-19 | 2026-03-27 | 2026-06-19 | — | [24 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-124 | Clean Up Return Loads | Highest | 200 | 2026-03-27 | 2026-06-19 | 2026-03-27 | 2026-06-19 | — | [24 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-83 | Customer Master Data Cleanup | High | 1480 | 2025-10-14 | 2026-06-01 | 2025-10-14 | 2026-06-01 | — | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-48 | System Connection Syteline-VKS | High | 240 | 2026-02-15 | 2026-06-30 | 2026-02-15 | 2026-06-30 | — | [18 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-68 | Catalog API Rust2Python | High | 640 | 2025-11-17 | 2026-04-24 | 2025-11-17 | 2026-04-24 | — | [5 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-43 | Data Security - Microsoft Purview | High | 0 | 2026-02-02 | 2026-06-30 | 2026-02-02 | 2026-06-30 | — | [16 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-19 | Changes to AR Aging Report | High | 120 | 2026-02-23 | 2026-04-17 | 2026-02-23 | 2026-04-17 | — | [19 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-49 | Marketing: STE Rewards Tier | Medium | 240 | 2026-03-27 | 2026-06-19 | 2026-04-03 | 2026-06-26 | +1 wk | [24 empty] | · | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-7 | Outsourced Unit Core Accounting | Medium | 640 | 2026-03-27 | 2026-06-19 | 2026-05-15 | 2026-08-07 | +7 wk | [24 empty] | · | · | · | · | · | · | · | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-52 | SWIMS/Syteline Reporting | Medium | 40 | 2026-03-27 | 2026-06-19 | 2026-04-24 | 2026-07-17 | +4 wk | [24 empty] | · | · | · | · | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-16 | Partial Pay w/ CC from WMERP | Medium | 120 | 2026-03-27 | 2026-06-19 | 2026-05-22 | 2026-08-14 | +8 wk | [24 empty] | · | · | · | · | · | · | · | · | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
ETE-100 | ATSG Expired Members Self-Payment | Medium | 200 | 2026-03-27 | 2026-06-19 | 2026-06-05 | 2026-08-28 | +10 wk | [24 empty] | · | · | · | · | · | · | · | · | · | · | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■
LEGEND
🔴 Red bar = Highest priority | Scheduled first, never shifted
🟡 Yellow bar = High priority | Scheduled second, no shifts needed here
🔵 Blue bar = Medium priority | Shifted right if needed to resolve overloads
🟩 Green dots = Original position | Where the project was before leveling pushed it
POST-LEVELING PEAK UTILIZATION
Role | Peak / Status
BA/SME | 21% 🟢
Functional | 49% 🟢
Technical | 21% 🟢
Developer | 32% 🟢
Infrastructure | 40% 🟢
DBA | 100% 🟡 At Limit — consider adding 1 DBA
PM | 35% 🟢

## AI_Agent_Spec
ETE IT PMO — AI Resource Planning Agent: Technical Specification
Phase 1 MVP — Stateful AI agent for resource optimization, portfolio analysis, and decision support.
1. PROJECT OVERVIEW
Project Name | ETE IT PMO AI Resource Planning Agent
Version | Phase 1 MVP
Purpose | Build a persistent AI agent that reads the ETE IT PMO Excel workbook, understands the project portfolio and team capacity, runs constraint-based optimization for resource scheduling, and provides natural language recommendations via a chat interface. Excel remains the source of truth for data entry and executive/board reporting.
Problem Statement | The PMO team manually manages 40+ projects across 23 resources using Excel. Determining optimal project schedules, identifying resource bottlenecks, and running what-if scenarios requires navigating 6+ interconnected sheets with complex formulas. The team needs an intelligent layer that can answer capacity questions, flag risks, and recommend optimal schedules — while keeping Excel as the foundation.
Key Outcome | A PMO lead can ask: "Can we take on a new 400-hour project with 60% Developer allocation?" and get an immediate answer with impact analysis, trade-off options, and a recommended schedule — all grounded in real data from the Excel workbook.
Estimated Effort | 2-3 weeks with one Python developer familiar with APIs and basic cloud deployment.
Estimated Monthly Cost | ~$30-70/month (Claude API ~$20-50, hosting ~$10-20). No per-seat licensing.
2. EXCEL DATA MODEL — Source of Truth
Workbook | ETE_2026_IT_Budget_Tracker.xlsx (hosted on SharePoint/OneDrive)
Access Method | Option A: Microsoft Graph API (if on SharePoint — preferred for real-time access) Option B: openpyxl (Python library — reads .xlsx directly from file share) Option C: OneDrive sync + file watcher (simplest — watch local copy for changes)
2a. Project Portfolio Sheet
Range | Project Portfolio'!A3:AC42 (row 3 = headers, rows 4-42 = projects)
Key Columns | A: ID (e.g., ETE-83) ¦ B: Project Name ¦ C: Type ¦ D: Business Portfolio ¦ E: Sponsor/Leader ¦ F: Project Health (ON TRACK, NEEDS SPEC, NOT STARTED, POSTPONED) ¦ G: % Complete (0-100%) ¦ H: Priority (Highest/High/Medium/Low) ¦ I: Start Date ¦ J: Est. End Date ¦ R: Est. Hours ¦ T-AA: Role allocation percentages (BA%, Func%, Tech%, Dev%, Infra%, DBA%, PM%, WMS%)
Active Filter | Exclude: Project Health = POSTPONED, % Complete = 100%. Currently ~13 active of 40 total.
Priority Rule | ABSOLUTE: Highest > High > Medium > Low. Never delay Highest for Medium.
2b. Team Roster Sheet
Range | Team Roster'!A3:H26 (23 team members)
Key Columns | A: Resource name ¦ B: Role (PM, DBA, BA, Functional, Technical, Developer, Infrastructure, WMS) ¦ C: Team ¦ D: Vendor ¦ E: Classification (FTE/Contractor) ¦ F: Rate/Hour ¦ G: Weekly Hrs Available ¦ H: Support Reserve %
Current Team | 23 resources: 3 PM, 1 DBA, 4 BA/SME, 2 Functional, 5 Technical, 4 Developer, 3 Infrastructure, 1 WMS
2c. RM_Assumptions Sheet
Time Allocation | Admin 10% + Break/Fix 10% + Project 80% = 100%. Result: 32 project hrs/person/week.
SDLC Phase Weights | Discovery 10%, Planning 10%, Design 15%, Build 30%, Test 20%, Deploy 15% = 100%
Role Effort Matrix | 8 roles × 6 phases. Example: Developer = 0% Discovery → 5% Planning → 10% Design → 50% Build → 25% Test → 10% Deploy. This drives demand curves — each role's workload varies by project phase.
Critical Rule | Demand for a role is ZERO if the project's role allocation % is 0 in the Portfolio. The agent MUST gate by this — we caught a bug where the Excel model was applying DBA effort to all projects regardless of allocation.
3. AGENT CAPABILITIES
3a. Core (MVP)
Portfolio Status | Answer: "What's the status of Highest projects?" "Which projects are stuck?" "How many projects does Tom lead?" Grounded in live Excel data.
Capacity Analysis | Calculate real-time utilization by role. Weekly supply = headcount × 32. Weekly demand = Σ(Est.Hours × Role% × SDLC Phase Effort%) / duration. Thresholds: <80% green, 80-99% yellow, ≥100% red.
What-If Scenarios | "What if we add a 400-hr project?" → adds demand, identifies overloaded weeks, generates 2-4 mitigation options with specific numbers.
Schedule Optimization | Sort by priority. Place projects on timeline. If any role exceeds 85%, shift lower-priority projects forward until it fits. Never shift Highest/High. Output: recommended dates + shift amounts.
Trade-Off Options | When constrained, generate 2-4 options: (A) delay specific projects, (B) add headcount + cost est., (C) reduce scope, (D) accept short overload. Rank by recommendation.
Change Detection | Compare current Excel to last snapshot. Report: new projects, status changes, % complete changes, date changes. Proactive at start of each session.
3b. Stretch (Phase 1.5)
Board Summary | Generate plain-English executive summary: active projects, utilization, top risks, decisions made. Write to Excel sheet.
Proactive Alerts | Teams/Slack notification when: role > 90%, project stuck > 2 weeks, end date passed with < 90% complete.
Trend Analysis | "How has Developer utilization trended over 8 weeks?" Requires storing weekly snapshots.
4. TECHNICAL ARCHITECTURE
Runtime | Python 3.11+, long-lived process (server, Azure Function, or local PC)
AI Model | Claude Sonnet 4 (claude-sonnet-4-20250514) via Anthropic API with tool-use
Optimization | Google OR-Tools (free, handles constraint programming). Objective: minimize total delay, constraints: all roles ≤ 85% utilization, priority hierarchy respected.
Memory | SQLite database. Tables: portfolio_snapshots (weekly state), decisions (approved actions + reasoning), agent_state (preferences, last run date).
Chat Interface | Option A: Streamlit web app (fastest to build, ~50 lines). Option B: Teams bot (best adoption, needs Azure AD setup).
Excel Access | openpyxl for direct file read/write. NEVER overwrite Portfolio or Team Roster without explicit user confirmation. Write only to output sheets.
5. SYSTEM PROMPT (Draft)
System Prompt | You are the ETE IT PMO Resource Planning Agent. You help the PMO team make data-driven resource allocation decisions. RULES: • Highest priority = immovable. Never delay. • High priority = minimal flex (≤2 weeks). • Medium/Low = flexible. Delay these first. • Target utilization: 85%. Red ≥100% must be resolved. • Demand = Est.Hours × Role% × SDLC Phase Effort% / Duration. Only if Role% > 0. • Always provide 2-4 concrete options with specific numbers. • Never overwrite source sheets without confirmation. • Lead with the answer, then supporting detail. • Cite specific numbers: "Developer at 106%" not "Developer is overloaded".
6. IMPLEMENTATION PLAN
Week 1: Foundation | Day 1-2: Excel Connector (read_portfolio, read_roster, read_assumptions) Day 3-4: Claude API + tool-use integration + system prompt Day 5: Memory store (SQLite, save/load/compare snapshots)
Week 2: Intelligence | Day 6-8: OR-Tools optimization engine (constraint solver for scheduling) Day 9-10: What-if scenario engine (add project, lose resource, shift dates)
Week 3: Interface | Day 11-12: Streamlit chat UI or Teams bot Day 13-14: End-to-end testing with real data (5 core scenarios) Day 15: Deployment + team training
7. SUCCESS CRITERIA
Accuracy | Utilization calculations match Excel within 1% tolerance.
Speed | All queries answered in <10 seconds (Excel read + Claude API + optimization).
Memory | Correctly identifies changes between sessions unprompted.
Optimization | All roles ≤85% in leveled schedule. No Highest project delayed. Total delay minimized.
Adoption | PMO lead uses agent ≥3x/week within 2 weeks of deployment.
Board Ready | Agent-generated summary needs <5 min of editing for board deck.
8. RISKS & MITIGATIONS
Stale Data | If Excel not saved/synced, agent reads old data. Mitigation: show "Data as of: [timestamp]" in every response.
AI Hallucination | Agent could generate plausible wrong numbers. Mitigation: every claim must trace to a tool call with cited source data.
Accidental Overwrite | Agent writes to wrong cells. Mitigation: hard-code whitelist of writable sheets (RM_Gantt, Board_Summary). Require confirmation.
Impractical Schedule | Algorithm shifts project 16 weeks. Mitigation: cap max shift by priority (Highest:0, High:2, Medium:8, Low:16 weeks).
Adoption Risk | Team doesn't use it. Mitigation: start with PMO lead only, prove value, then expand. Excel stays primary interface.